## Standup Notes
| sprint 1-wk1 | may vakantie | sprint 2-wk2 | sprint 0-wk3 | sprint 1-wk4 | sprint 1-wk5 | sprint 2-wk6 | sprint 2-wk7 | sprint 2-wk8 | end
2.4 IT CORP | 2021-04-30 | 2021-05-07 | 2021-05-14 | 2021-05-21 | 2021-05-28 | 2021-06-04 | 2021-06-11 | 2021-06-18 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29
Scrum Master | keith | mykhailo g | yang | jane | tuan | sefanja | mykhailo g | keith | yang
yang | 2021-04-30: survey questions, customer journey map, worked on PoA; 2021-05-07: Activity map ,BPMN, worked on PoA; 2021-05-14: Rest API design; 2021-05-21: (issue#13) Implement Vue login page& register page; 2021-05-28: Update API, Implement Fetch API connection (login page & register page) with backend; 2021-06-04: (issue#15) Implement news function
jane | 2021-04-30: worked on plan of approach; 2021-05-07: worked on plan of approach; 2021-05-14: worked on plan of approach
tuan | 2021-04-30: Checking requirements, brainstorming ideas, research project materials; 2021-05-07: Updating survey, worked on delivery document, worked on PoA; 2021-05-14: Finished PoA, brainstorming main module to focus on, finalized documents; 2021-05-21: researched and make a demo project for vuejs; 2021-05-28: worked on vuejs demo webapp; 2021-06-04: Finalized deliverables for 1st sprint
sefanja | 2021-04-30: Discuss the projects, brainstorm ideas and come up with survey questions.; 2021-05-07: Brainstorm results of survey.; 2021-05-14: Design the first concept wireframes for the project and discuss them with the team and client.; 2021-05-21: New feedback that the project has and add them to the design and more wireframes. Start with Vue.; 2021-05-28: Finalize the design and wireframes with all functions and continue learning with Vue.
mykhailo g | 2021-04-30: checked the project requirement one more time.; 2021-05-07: Updated survey. Found and implemented a base project. Worked on PoA.; 2021-05-14: Created a different base project because previous didn't work on all computers.; 2021-05-21: Implemented sql lite for our project. Fixed bugs with teammates.; 2021-05-28: implemented homepage from wireframes using HTML CSS Vue.js
keith | 2021-04-30: check details of project. discuss project. Setup git repository; 2021-05-07: work on survey. Create working document. Looked for base project that uses Vue; 2021-05-14: create timesheet. Create standup notes file. Created remote mysql db; 2021-05-21: created vue-app2 as base project; 2021-05-28: helping others getting vue-app2 installed on their computers. work on plan of approach; 2021-06-04: finalized plan of approach. Started with vue project.