## Standup Notes
| sprint 1-wk1 | may vakantie | sprint 2-wk2 | sprint 0-wk3 | sprint 1-wk4 | sprint 1-wk5 | sprint 2-wk6 | sprint 3-wk7 | sprint 3-wk8 | end
2.4 IT CORP | 2021-04-30 | 2021-05-07 | 2021-05-14 | 2021-05-21 | 2021-05-28 | 2021-06-04 | 2021-06-11 | 2021-06-18 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29
Scrum Master | keith | mykhailo g | yang | jane | tuan | sefanja | mykhailo g | keith | yang
yang | survey questions, customer journey map, worked on PoA | Activity map ,BPMN, worked on PoA | Rest API design | (issue#13) Implement Vue login page& register page | Update API, Implement Fetch API connection (login page & register page) with backend | (issue#15) Implement news function | Team is divided, Mykhailo and I completed the remaining issues of sprnt2. | focusing on completing the quiz, video, and discussion pages, the realization of some functions: automatic scoring in quiz, calculation in spidermap, and download functions... etc. .Learned and used vuex store | worked on api connection, final document and improve cod.
jane | 2021-04-30: worked on plan of approach; 2021-05-07: worked on plan of approach; 2021-05-14: worked on plan of approach
tuan | 2021-04-30: Checking requirements, brainstorming ideas, research project materials; 2021-05-07: Updating survey, worked on delivery document, worked on PoA; 2021-05-14: Finished PoA, brainstorming main module to focus on, finalized documents; 2021-05-21: researched and make a demo project for vuejs; 2021-05-28: worked on vuejs demo webapp; 2021-06-04: Finalized deliverables for 1st sprint
sefanja | 2021-04-30: Discuss the projects, brainstorm ideas and come up with survey questions.; 2021-05-07: Brainstorm results of survey.; 2021-05-14: Design the first concept wireframes for the project and discuss them with the team and client.; 2021-05-21: New feedback that the project has and add them to the design and more wireframes. Start with Vue.; 2021-05-28: Finalize the design and wireframes with all functions and continue learning with Vue.
mykhailo g | checked the project requirement one more time. | Updated survey. Found and implemented a base project. Worked on PoA. | Created a different base project because previous didn't work on all computers. | Implemented sql lite for our project. Fixed bugs with teammates. | implemented homepage from wireframes using HTML CSS Vue.js | Created all issues on GitLab that we discussed with the team and the client. Started putting home page tiles in Vue components. The homepage implementation doesn't look very good, so we're going to fix that. | The team is divided so, Yang and I will finish the initial project. Implemented some of the components for the home page. The main focus, for now, is to complete all of the open issues on Gitlab and start working on the sprint 2 delivery document. | After the conversation with the client, it is clear that we are heading in the right direction. I'm in the process of connecting everything to API. And implementing the peer study functionality requested by the customer | Preparing for the presentation. I'll be working on the refactoring the code and finalizing the documentation after the presentation.
keith | 2021-04-30: check details of project. discuss project. Setup git repository; 2021-05-07: work on survey. Create working document. Looked for base project that uses Vue; 2021-05-14: create timesheet. Create standup notes file. Created remote mysql db; 2021-05-21: created vue-app2 as base project; 2021-05-28: helping others getting vue-app2 installed on their computers. work on plan of approach; 2021-06-04: finalized plan of approach. Started with vue project.